# Outage project notes (April 2nd)

# Outage schedulers challenges

I’ll structure this in three parts:

- What makes outage scheduling uniquely hard

- Where current CPM + resource leveling breaks down

- How your RCPSP + SGS + Genetic Programming priority engine could realistically help

What Makes Nuclear Outage Scheduling So Difficult

A refueling or maintenance outage is not just a large project — it’s an extremely constrained, high-risk, multi-organizational optimization problem.

Here are the real challenges we face:

A. Extreme Resource Contention (Not Just Quantity — Qualifications)

We don’t just schedule “electricians.”
We schedule:

- RP technicians (radiation protection)

- I&C technicians

- Certified welders (nuclear-grade)

- Scaffold builders

- Containment entry supervisors

- QA inspectors

- System engineers

- Operations for tag-outs

- Crane operators (specific cranes)

Constraints include:

- Union rules

- Fatigue rules (max hours/week)

- Radiation exposure limits

- Certification constraints

- Badge access & clearance

- Shift structure (day/night split)

- Shared resources across parallel work fronts

Pain point: CPM gives a critical path ignoring skill-constrained bottlenecks. Resource leveling after-the-fact often destroys the logic of the schedule.

B. Space Conflicts (Physical Interference)

Multiple crews cannot work in the same:

- Containment elevation

- Steam generator manway

- Valve vault

- Refueling cavity

- Turbine deck zone

We constantly face:

- Scaffold conflicts

- Crane swing conflicts

- Heavy load path conflicts

- Congestion risks

Pain point: These are rarely modeled explicitly in CPM. They are “tribal knowledge” constraints.

C. Radiation & ALARA Optimization

We must:

- Minimize person-rem exposure

- Sequence high-dose work efficiently

- Avoid rework entries

- Reduce congestion in high-dose areas

Pain point: CPM minimizes duration — not dose accumulation or congestion-based exposure.

D. System State Dependencies (Not Just Precedence)

Some tasks require:

- System drained

- System depressurized

- Containment open

- Specific plant modes

- Outage risk windows

Many tasks could be done in different modes, but some modes are very expensive in time.

Pain point: Logical precedence ≠ optimal sequencing for plant state management.

E. Emergent / Discovery Work

During outage:

- Valve fails inspection

- Pump impeller damage

- Foreign material found

- Additional weld repairs required

We must:

- Insert emergent work

- Protect the critical path

- Reallocate constrained craft

Pain point: Schedules are fragile. Priority heuristics matter more than deterministic optimization.

F. Multi-Contractor Coordination

We deal with:

- Utility core staff

- Long-term vendors

- Short-term specialty crews

- OEM reps

- Regulatory hold points

Each has:

- Different productivity rates

- Different availability windows

- Contractual milestones

Where Traditional CPM + Leveling Fails Us

Even with resource leveling:

| Issue | What Happens |
| --- | --- |
| Critical path shifts daily | Due to resource constraints |
| “Near critical” paths ignored | But become critical when resources constrained |
| Serial SGS bias | Tends to overload early periods |
| Parallel SGS bias | Can starve critical chain if priority rule is weak |
| Static priority rules | Don’t reflect outage strategy |

Typical priority rules we use:

- Minimum slack

- Shortest processing time

- Most successors

- Highest risk tasks first

But these are crude.

How Your RCPSP + SGS + Genetic Programming Could Help

Now I’ll evaluate your approach from a scheduler’s perspective.

You propose:

- RCPSP model

- Serial + Parallel SGS

- Genetic Programming to evolve activity priority rules

That’s interesting — because in outages:

Priority logic is everything.

A. Genetic Programming for Priority Rule Evolution

Instead of fixed heuristics like:

- Min slack

- Max successors

- Earliest start

You evolve priority expressions like:

Priority(activity i) = f(slack_i, dose_i, craft scarcity_i, system state penalty_i, congestion_i, risk_i)

That could help with:

1. Craft Bottleneck Management

If GP learns:

- Scarce resource tasks must be front-loaded

- Or clustered efficiently

It may reduce late congestion of:

- RP techs

- I&C techs

- QA inspectors

This is huge.

2. Radiation Dose Optimization

If you embed:

- Radiation field intensity

- Work duration

- Crew size

- Spatial congestion

GP could learn to:

- Sequence high-dose tasks tightly

- Reduce repeated entries

- Minimize total collective dose

That’s something CPM cannot do.

3. Congestion & Spatial Awareness

If you encode:

- Location ID

- Zone capacity

- Simultaneous crew limits

GP could evolve:

- “Avoid stacking high crew density tasks”

- “Cluster tasks by elevation”

This mimics experienced outage planners.

4. Dynamic Criticality Recognition

Classic CPM only tracks float.

But in outage reality:

- Resource criticality > logic criticality

GP may learn that:

- Tasks requiring rare welders are “functionally critical”

- Even if they have float in logic network

This reflects reality better.

5. Emergent Work Absorption

If your system can:

- Re-run SGS quickly

- Re-evolve or apply trained priority logic

It could:

- Insert emergent tasks

- Re-sequence automatically

- Protect critical milestone (breaker close)

That’s very powerful.

Where I’d Challenge Your Model (As a Scheduler)

If I were evaluating your tool, I would ask:

1. Can You Model Multi-Skill Crews?

Example:

- 1 welder + 1 helper + 1 RP tech required simultaneously.

Classic RCPSP struggles with multi-skill resource bundles.

2. Can You Model Shift Boundaries?

Outage reality:

- Some tasks cannot start at 10 PM

- Some require full continuous shift

- Hand-offs cause inefficiencies

Is your SGS time-continuous or shift-aware?

3. Can You Penalize Schedule Nervousness?

If GP constantly shifts task order drastically,
field supervisors will reject it.

We value:

- Stability

- Minimal resequencing

4. Can You Incorporate Risk Windows?

For example:

- Containment open time is extremely expensive

- Reactor vessel head removal window

Does your fitness function penalize:

- Mode extension

- Regulatory exposure

What Would Make This Tool Truly Valuable

From an outage scheduler’s perspective, your tool becomes powerful if it can:

✔ Optimize for multiple objectives:

- Outage duration

- Resource smoothness

- Radiation dose

- Congestion

- Risk exposure

- System mode penalties

✔ Learn from historical outages

Train GP using:

- Past outage data

- Known good schedules

- Delay patterns

✔ Provide Explainable Priority Rules

If GP evolves:
Priority = 0.4*(1/slack) + 0.3*(craft scarcity) + 0.2*(dose rate) …

I need to understand it.

Black-box optimization will not be trusted in nuclear.

Big Picture Assessment

Your approach is promising because:

Outage scheduling is not just a network problem.
It is a priority assignment problem under extreme constraints.

RCPSP + SGS handles feasibility.
Genetic Programming handles intelligence.

That’s a strong combination.

# Additional challenges

1. The Dimensionality of Constraints

In a typical refueling outage (RFO), I am managing 10,000 to 15,000 activities in a three-week window.

- The Challenge: Traditional Critical Path Method (CPM) tools are great for logic, but they are terrible at "Leveling." I often have 500 tasks requiring the same specialized radiation protection (RP) technician or a specific overhead crane.

- How your tool helps: By using Serial and Parallel SGSs, your tool doesn't just tell me when a task could happen; it tells me when it can happen based on actual headcount. This prevents the "phantom schedule" where 50 people are assigned to a room that only fits 10.

2. Spatial and Environmental Interference

In a containment building, space is a finite resource.

- The Challenge: I might have the parts and the people for two different pump overhauls, but if they are located in the same physical cubicle, they cannot happen simultaneously. Furthermore, "high-dose" areas limit how long a crew can stay on-station.

- How your tool helps: If your Genetic Programming model can incorporate "Spatial Constraints" or "Dose Logic" into the activity priority assessment, it would be revolutionary. It could prioritize the high-dose work during periods where RP support is at its peak.

3. The "Discovery Work" Chaos

An outage is a living organism. We open a valve for inspection and find unexpected corrosion. Suddenly, a 4-hour task becomes a 48-hour repair.

- The Challenge: My current schedule becomes "stale" the moment discovery work starts. Re-leveling the entire schedule manually takes hours, and by the time I’m done, the field conditions have changed again.

- How your tool helps: This is where Genetic Programming shines. If your GP can evolve priority rules that favor Robustness (schedules that don't fall apart when one task slips) rather than just Makespan (the shortest possible time), I gain a "buffer" against the unknown.

4. Technical Specifications and Safety Functions

Nuclear scheduling isn't just about finishing fast; it's about maintaining Defense in Depth.

- The Challenge: I must ensure that I never take two redundant safety systems (e.g., Emergency Diesel Generators) out of service at the same time. This logic is often "hidden" in the scheduler's head or complex "look-ahead" spreadsheets.

- How your tool helps: By coupling RCPSP with GP, you can assign an "Infinite Penalty" to any schedule sequence that violates a Tech Spec or a safety function. The GP will learn to never even suggest a priority list that leaves the core vulnerable.

Comparison of Scheduling Approaches

| Feature | Traditional CPM | Your RCPSP + GP Approach |
| --- | --- | --- |
| Resource Limits | Manual "Leveling" (Often ignored) | Hard Constraints via SGS |
| Priority Logic | Static (Total Float) | Dynamic (Evolved via GP) |
| Complexity | Becomes unmanageable >5k tasks | Scalable through automated heuristics |
| Adaptability | High manual effort to update | Rapid re-optimization for "Discovery Work" |

Export to Sheets

My "Outage Resident" Perspective

The most valuable thing your tool provides me isn't a "perfect" schedule—it's options. If the GP can provide me with three different schedule "evolutions" (e.g., one optimized for minimum dose, one for minimum duration, and one for maximum resource stability), I can take those to the Outage Manager and make an informed, data-driven decision.

One final piece of advice: Ensure your tool can handle "Calendars" for specific resources. In nuclear, some crews only work day shifts, while others are 24/7. If your SGS can't account for the 12-hour shift handover, the field teams will lose trust in the tool within the first 48 hours.