## Sheet1
Domain | Class | Type | Definition | Key_Attributes | Required | Primary_Data_Sources | Example_Values | Notes
OutageExecution | Outage | Node | A specific outage campaign for a plant unit | outage_id; plant_id; unit_id; outage_type; planned_start; planned_end; actual_start; actual_end; baseline_duration_hours; actual_duration_hours | Yes | Outage schedule; outage planning package; outage closeout reports | RFO-2026-U1; PlantA; Unit1; Refueling | Root context for all outage analytics
OutageExecution | OutagePhase | Node | A major phase within an outage | phase_id; phase_name; planned_start; planned_end; actual_start; actual_end | Yes | Outage schedule; outage milestone plan | PH-05; Startup | Supports phase-specific risk and schedule analysis
OutageExecution | Activity | Node | A planned or emergent outage activity | activity_id; activity_name_raw; activity_name_normalized; activity_type; role_id; craft; planned_start; planned_end; actual_start; actual_end; duration_hours; schedule_status; critical_path_flag; float_hours; data_quality_score | Yes | Outage activity logs; planned and actual schedules; emergent work list | ACT-002188; Replace leaking valve; emergent; MECH | Extends the original report activity concept
OutageExecution | Milestone | Node | A high-level outage checkpoint | milestone_id; name; planned_date; actual_date; status | No | Outage milestone schedule | MS-12; Critical Path Complete | Useful for executive summary outputs
OutageExecution | DelayEvent | Node | A schedule delay instance affecting one or more tasks | delay_id; delay_start; delay_end; delay_hours; delay_type; delay_reason_text; confirmed_flag | Yes | Schedule variance logs; outage execution reports | DLY-45; 6.5; resource delay | Separates delay from activity to preserve schedule traceability
PlantStructure | Plant | Node | A nuclear generating station | plant_id; plant_name; site_name; reactor_type; operator | Yes | Plant master data | PLT-01; Byron; PWR | Top-level physical context
PlantStructure | Unit | Node | A generating unit within a plant | unit_id; unit_name; unit_number; rated_power_mwe | Yes | Plant/unit master data | UNIT-1; Unit 1; 1 | Linked to outage instances
PlantStructure | System | Node | A plant system | system_id; system_name; system_code; system_class; safety_significance; risk_significance | Yes | Equipment hierarchy; design basis; EAM/CMMS | SYS-FW; Feedwater | Core aggregation object for risk rollup
PlantStructure | Subsystem | Node | A lower-level functional grouping within a system | subsystem_id; subsystem_name; subsystem_code | No | Equipment hierarchy | SS-FW-VLV; Feedwater valve train | Optional if hierarchy is available
PlantStructure | Component | Node | A specific maintainable equipment item | component_id; plant_tag; component_type; description; manufacturer; model; serial_number; install_date; criticality; location; status | Yes | Equipment master; CMMS/EAM; tag list | CMP-8821; FW-VLV-102; motor-operated valve | Generalizes plant_element_id into canonical asset object
PlantStructure | Location | Node | A physical plant location | location_id; area_name; elevation; building; radiological_zone | No | Plant location master; ALARA maps | LOC-212; Turbine Building 2nd Floor | Useful for access and execution constraints
PlantStructure | Procedure | Node | A plant procedure or work instruction | procedure_id; procedure_number; title; revision; status | No | Procedure management system | OP-123; Valve Stroke Test; Rev 8 | Often referenced in work text
PlantStructure | DocumentedIdentifier | Node | A raw identifier extracted from text that may refer to equipment; procedure; document; local alias | identifier_value; identifier_type; source_system; confidence; normalized_value | Yes | NLP extraction; raw text logs; CMMS exports | 1FW-102A; equipment_tag; 0.84 | Critical when plant data is messy or incomplete
Reliability | ConditionReport | Node | A condition report or CAP issue documenting a problem | cr_id; title; description_raw; detected_date; discovery_method; priority; status; apparent_cause; root_cause; corrective_action_summary; data_quality_score | Yes | CAP/CR system; issue database | CR-24811; Leakage observed on FW valve | Primary causal evidence source
Reliability | WorkOrder | Node | A maintenance or corrective work order | wo_id; wo_type; description; creation_date; planned_date; completion_date; maintenance_type; priority; status | Yes | CMMS/EAM work management | WO-55219; Corrective; Replace packing | Extends original report work_order concept
Reliability | MaintenanceEvent | Node | Execution instance of a maintenance action | maintenance_event_id; event_type; execution_start; execution_end; as_found_condition; as_left_condition; effectiveness_rating; rework_flag | No | Work order closeout; maintenance history | ME-9901; PM; degraded; acceptable | Important for repeat-failure and maintenance-effectiveness analysis
Reliability | InspectionEvent | Node | Execution instance of an inspection or surveillance | inspection_id; inspection_type; inspection_date; result; finding_summary; pass_fail | No | Inspection system; surveillance logs | INSP-202; VT; minor leakage | Useful precursor source
Reliability | FailureMode | Node | Specific manner in which a component fails | failure_mode_id; name; domain; severity_class; taxonomy_source | Yes | CR coding; reliability database; NLP classification | FM-LEAK; Leakage | Bridges plant text to reliability reasoning
Reliability | DegradationMechanism | Node | Underlying degradation process | degradation_id; name; mechanism_family; description | No | Engineering reliability docs; failure analysis reports; CR text | DG-CORR; Corrosion | Needed for stronger causal modeling
Reliability | AnomalyEvent | Node | Observed abnormal condition that may precede outage work | anomaly_id; event_time; description; anomaly_type; severity; source_type; confidence_score | No | Condition monitoring; operator logs; CRs; maintenance notes | AN-777; abnormal vibration; medium | Flexible event node for precursor patterns
Reliability | CorrectiveAction | Node | Planned or completed action responding to a condition issue | ca_id; description; owner; due_date; completion_date; status; effectiveness_review | No | CAP/CR system | CA-1221; Replace packing during outage | Connects issue history to action history
ScheduleOps | ScheduleTask | Node | A task from the outage planning system | task_id; task_name; wbs_code; planned_start; planned_finish; actual_start; actual_finish; total_float; critical_path_flag; status | Yes | Primavera/P6 or equivalent schedule export | TASK-STARTUP-17; Perform startup test | Core node for operational integration
ScheduleOps | Dependency | Node | A logical dependency between schedule tasks | dependency_id; dependency_type; lag_hours; hard_constraint_flag | Yes | Schedule logic export | DEP-109; FS; 4 | Supports propagation of delay impact
ScheduleOps | Resource | Node | A crew; contractor; or execution resource | resource_id; resource_type; organization; crew_size; availability_window; qualification_level | No | Resource loading sheets; contractor staffing plans | RES-MECH-A; mechanic crew; 5 | Needed for feasibility and staffing constraints
ScheduleOps | Constraint | Node | Operational; safety; radiological; tooling; access; or configuration limitation | constraint_id; constraint_type; description; active_start; active_end; severity; owner | No | ALARA plans; outage constraints log; work package notes | CON-88; scaffold required | Explains schedule risk beyond equipment condition
ScheduleOps | WorkWindow | Node | An approved execution window tied to access or plant configuration | window_id; window_type; start_time; end_time; approval_status | No | Operations schedules; clearance windows | WW-43; clearance window | Useful in highly constrained outage execution
ScheduleOps | Clearance | Node | A lockout; tagout; or equipment clearance state | clearance_id; clearance_number; issue_time; release_time; status | No | Operations clearance system | CL-4012 | Often acts as a direct schedule prerequisite
Prediction | RiskScenario | Node | A modeled outage risk context | scenario_id; scenario_name; scope_level; prediction_window; generated_time; model_context | Yes | Derived from graph analytics and model execution | SCN-2026-01; Startup feedwater risk | Groups related predictions
Prediction | RiskPrediction | Node | A predicted outage-relevant event or impact | prediction_id; target_type; target_id; predicted_event_type; probability; expected_delay_hours; delay_p10; delay_p50; delay_p90; model_version; confidence_score | Yes | Predictive model outputs | RP-2026-007; Component; 0.42; 11.5 | Central object for decision support
Prediction | Recommendation | Node | A suggested action to reduce outage risk | recommendation_id; recommendation_type; priority; action_text; expected_benefit_hours; generated_time; acceptance_status; owner | Yes | Decision engine output; engineering review | REC-88; pre-outage replacement; high | Turns analysis into action
Prediction | ContingencyPlan | Node | A schedule or resource contingency tied to a risk scenario | plan_id; description; contingency_hours; resource_reserve; trigger_condition | No | Outage planning process; decision engine | CP-14; Add 8h startup contingency | Operational planning output
Prediction | RiskRegisterEntry | Node | A ranked manager-facing outage threat summary | entry_id; rank; risk_score; summary; status; last_reviewed | No | Derived dashboard output | RRE-12; 2; 0.71 | Good summary abstraction for dashboards
Provenance | SourceRecord | Node | Metadata record for where a fact came from | source_id; source_system; document_type; record_key; ingestion_time; author; revision | Yes | All source systems | SRC-CR-24811; CAP system | Required for traceability
Provenance | Extraction | Node | A machine-generated extraction from text or semi-structured data | extraction_id; method; confidence_score; review_status; extract_time | Yes | NLP pipeline; rules engine | EXT-992; dictionary+NER; 0.73 | Makes imperfect extraction explicit
Provenance | Evidence | Node | A record; text snippet; or signal supporting a fact; relation; or prediction | evidence_id; evidence_type; evidence_text; timestamp; confidence_score; reviewed_flag | Yes | CR text; WO closeout text; schedule notes; monitoring signals | EVD-77; text_snippet | Critical for explainability and human trust
Provenance | DataQualityAssessment | Node | Structured evaluation of data quality for a record or source | dqa_id; completeness_score; consistency_score; timeliness_score; ambiguity_score; overall_score; issue_summary | Yes | Derived data quality checks | DQA-22; 0.81 | Should be first-class in this application
Provenance | HumanReview | Node | A human validation or correction of extracted facts or inferred relations | review_id; reviewer; review_time; decision; comment | No | Analyst/engineer workflow | HR-11; approved | Important for low-confidence high-impact cases
Semantic | DomainEntity | Node | Canonical semantic concept extracted from outage or maintenance text | entity_id; canonical_name; entity_class; subclass; synonyms; dictionary_source | Yes | Dictionary files; ontology tables; NLP extraction | ENT-VALVE; valve; component_term | Extends original report nuclear_entity concept
Semantic | Abbreviation | Node | Normalized abbreviation or alias used in plant text | abbr_id; raw_form; expanded_form; context; confidence | Yes | Custom dictionaries; text mining | ABR-18; vlv; valve | Matches the report preprocessing approach
Semantic | TextDocument | Node | A raw textual source used for extraction | document_id; document_type; title; raw_text; created_time; source_system | No | CRs; WOs; outage logs; reports | DOC-991; WO closeout note | Useful when preserving document-level lineage
Semantic | EntityOccurrence | Node | A specific mention of a semantic entity in text | occurrence_id; start_offset; end_offset; normalized_text; confidence | No | NLP pipeline | OCC-61; replace; 0.91 | Helpful when explainability must be precise
Relationships | HAS_UNIT | Edge | Plant contains unit | confidence_score | Yes | Plant master data | PlantA -> Unit1 | Structural relation
Relationships | HAS_OUTAGE | Edge | Unit undergoes outage | source_system | Yes | Outage planning and execution records | Unit1 -> RFO-2026-U1 | Structural relation
Relationships | HAS_PHASE | Edge | Outage includes phase | planned_start; actual_start | Yes | Outage schedule | RFO-2026-U1 -> Startup | Operational context
Relationships | INCLUDES_ACTIVITY | Edge | Outage contains activity | activity_classification_confidence | Yes | Outage activity logs | RFO-2026-U1 -> ACT-002188 | Core execution relation
Relationships | OCCURS_IN_PHASE | Edge | Activity executed in outage phase | time_overlap_score | Yes | Activity timestamps; phase windows | ACT-002188 -> Startup | Phase mapping may be inferred
Relationships | IMPLEMENTS_TASK | Edge | Activity maps to planning-system task | mapping_confidence | Yes | Schedule export; activity logs | ACT-002188 -> TASK-STARTUP-17 | Operational integration
Relationships | CAUSES_DELAY_TO | Edge | Activity delays schedule task | impact_hours; confidence_score | Yes | Variance logs; schedule updates | ACT-002188 -> TASK-STARTUP-17 | Critical schedule-impact relation
Relationships | CONTRIBUTES_TO_DELAY | Edge | Delay event affects outage duration | delay_hours | Yes | Delay logs; outage closeout | DLY-45 -> RFO-2026-U1 | Useful for rollup
Relationships | USES_RESOURCE | Edge | Activity uses crew or contractor resource | hours_used; resource_confidence | No | Resource plans; execution logs | ACT-002188 -> RES-MECH-A | Supports staffing analysis
Relationships | SUBJECT_TO_CONSTRAINT | Edge | Activity limited by constraint | severity; active_flag | No | Constraints log; work package notes | ACT-002188 -> CON-88 | Explains operational friction
Relationships | PRECEDES | Edge | Task sequencing relationship | dependency_type; lag_hours | Yes | Schedule logic export | TASK-A -> TASK-B | Schedule logic
Relationships | HAS_DEPENDENCY | Edge | Task references dependency object | source_system | No | Schedule export | TASK-STARTUP-17 -> DEP-109 | Optional modeling pattern
Relationships | PART_OF_SYSTEM | Edge | Component belongs to system | confidence_score | Yes | Equipment hierarchy | FW-VLV-102 -> Feedwater | Key aggregation relation
Relationships | PART_OF_SUBSYSTEM | Edge | Component belongs to subsystem | confidence_score | No | Equipment hierarchy | FW-VLV-102 -> Feedwater valve train | Optional
Relationships | LOCATED_IN | Edge | Component located in plant area | source_system | No | Location master | FW-VLV-102 -> Turbine Building | Supports field execution context
Relationships | GOVERNED_BY | Edge | Activity governed by plant procedure | reference_confidence | No | Procedure system; text extraction | ACT-002188 -> OP-123 | Often extracted from text
Relationships | HAS_IDENTIFIER | Edge | Component has raw or alternate identifier | identifier_status | Yes | Equipment master; NLP extraction | FW-VLV-102 -> 1FW-102A | Handles aliases
Relationships | REFERENCES_IDENTIFIER | Edge | Activity text contains identifier | extraction_confidence | Yes | NLP extraction | ACT-002188 -> 1FW-102A | Used before canonical resolution
Relationships | RESOLVES_TO | Edge | Raw identifier resolves to canonical component | resolution_confidence; resolution_method | Yes | Tag dictionary; engineer review | 1FW-102A -> FW-VLV-102 | Must preserve uncertainty
Relationships | REFERENCES_WORK_ORDER | Edge | Activity refers to a work order | extraction_confidence | Yes | Text extraction; work management data | ACT-002188 -> WO-55219 | Preserves original report concept
Relationships | MENTIONS_ENTITY | Edge | Activity text mentions semantic concept | count; confidence_score | Yes | NLP pipeline | ACT-002188 -> valve | Preserves original report concept
Relationships | HAS_OCCURRENCE | Edge | Document contains entity occurrence | extraction_method | No | NLP pipeline | DOC-991 -> OCC-61 | Optional provenance detail
Relationships | INSTANCE_OF | Edge | Entity occurrence maps to canonical entity | confidence_score | No | NLP pipeline | OCC-61 -> valve | Optional provenance detail
Relationships | SIMILAR_TO | Edge | Semantic entities are related | similarity_score; method | No | Dictionary curation; embeddings | valve -> MOV | Useful for generalization
Relationships | AFFECTS_COMPONENT | Edge | Condition report concerns component | mapping_confidence | Yes | CR system; NLP; tag mapping | CR-24811 -> FW-VLV-102 | Causal anchor
Relationships | INDICATES_FAILURE_MODE | Edge | CR implies or records failure mode | confidence_score | Yes | CR coding; NLP classification | CR-24811 -> Leakage | Bridges issue text to reliability model
Relationships | ARISES_FROM | Edge | Failure mode linked to degradation mechanism | causal_strength; evidence_count | No | Failure analysis; engineering knowledge | Leakage -> Packing wear | Supports deeper causal reasoning
Relationships | ADDRESSES_COMPONENT | Edge | Work order targets component | mapping_confidence | Yes | CMMS/EAM | WO-55219 -> FW-VLV-102 | Needed for maintenance linkage
Relationships | EXECUTES_WORK_ORDER | Edge | Maintenance event executes work order | completion_status | No | Work order closeout | ME-9901 -> WO-55219 | Optional but valuable
Relationships | INSPECTS_COMPONENT | Edge | Inspection examines component | inspection_result | No | Inspection systems | INSP-202 -> FW-VLV-102 | Useful precursor relation
Relationships | RESULTS_IN_CONDITION | Edge | Maintenance discovers or leaves condition | confidence_score | No | Closeout notes | ME-9901 -> AN-777 | Supports event chains
Relationships | DETECTED_BY | Edge | Anomaly detected by inspection | confidence_score | No | Inspection systems | AN-777 -> INSP-202 | Supports precursor evidence
Relationships | TRIGGERS_ACTIVITY | Edge | Anomaly led to outage work | temporal_gap_hours; confidence_score | No | Event reconstruction | AN-777 -> ACT-002188 | Important causal relation
Relationships | CAUSED_BY | Edge | Activity linked causally to prior condition report | causal_strength; confidence_score; reviewed_flag | Yes | CRs; work orders; temporal reconstruction | ACT-002188 -> CR-24811 | Must never be asserted without confidence
Relationships | LINKED_TO_CA | Edge | Condition report linked to corrective action | status | No | CAP system | CR-24811 -> CA-1221 | Useful for closure and effectiveness
Relationships | HAS_PREDICTION | Edge | Risk scenario contains prediction | generated_time | Yes | Model outputs | SCN-2026-01 -> RP-2026-007 | Prediction grouping
Relationships | TARGETS_COMPONENT | Edge | Prediction applies to component | probability; expected_delay_hours | Yes | Model outputs | RP-2026-007 -> FW-VLV-102 | Core decision-support relation
Relationships | TARGETS_SYSTEM | Edge | Prediction applies to system | probability; expected_delay_hours | No | Model outputs | RP-2026-010 -> Feedwater | System-level rollup
Relationships | TARGETS_PHASE | Edge | Prediction applies to phase | probability; expected_delay_hours | No | Model outputs | RP-2026-011 -> Startup | Phase-level rollup
Relationships | MITIGATES | Edge | Recommendation reduces predicted risk | expected_benefit_hours; confidence_score | Yes | Decision engine | REC-88 -> RP-2026-007 | Connects prediction to action
Relationships | IMPLEMENTS_PLAN | Edge | Contingency plan operationalizes recommendation | owner; status | No | Planning process | CP-14 -> REC-88 | Planning follow-through
Relationships | SUMMARIZES_RISK | Edge | Dashboard risk entry summarizes prediction | rank; risk_score | No | Dashboard layer | RRE-12 -> RP-2026-007 | Useful for UI abstraction
Relationships | DERIVED_FROM | Edge | Extraction came from source record | method | Yes | Ingestion and NLP pipeline | EXT-992 -> SRC-CR-24811 | Traceability
Relationships | SUPPORTS | Edge | Evidence supports a fact or prediction | confidence_score; reviewed_flag | Yes | Evidence assembly layer | EVD-77 -> CAUSED_BY | Explainability
Relationships | HAS_QUALITY_ASSESSMENT | Edge | Record has data quality evaluation | assessment_time | Yes | Data quality pipeline | ACT-002188 -> DQA-22 | Needed for data-aware analytics
Relationships | REVIEWS | Edge | Human reviewed node or relation | decision; comment | No | Human review workflow | HR-11 -> CAUSED_BY | Important for high-risk low-confidence facts