# Outage Similarity Notes

## Guidance to Improve the Similarity Approach

1. Move from text similarity to case-based similarity. Treat each historical activity as a case, not just a sentence. For each activity, build a feature vector with:

- cleaned task description

- work discipline or craft

- system/component family

- unit / plant / utility

- planned duration

- work order type

- outage phase or work window

- predecessor/successor context

- flags for scaffolding, RP hold points, inspections, testing, valve lineups, clearance dependencies

- crew size if available

- whether work was emergent or planned

- whether rework/finding occurred

Then similarity becomes a composite score, for example:

- text similarity: 30%

- task class/component similarity: 30%

- plant/unit/context similarity: 20%

- schedule neighborhood / dependency pattern similarity: 20%

The exact weights can be learned from historical forecast performance. This would make the tool behave more like an experienced planner, who never judges task similarity from words alone.

2. Use weighted retrieval, not a hard threshold. Instead of “all activities with similarity > 0.8,” use the top-k neighbors with relevance weights. That gives you:

- smoother behavior

- better handling of sparse classes

- less sensitivity to arbitrary cutoff choice

- a natural way to form empirical quantiles

You can still impose minimum quality rules, such as requiring at least a few moderately similar cases before trusting the result.

3. Build a task taxonomy first. The paper mentions labels, but about 30% of activities are unlabeled, and the labels are plant-specific. I would strongly recommend building a standard outage task ontology before pushing further on duration uncertainty. Even a modest hierarchy would help a lot:

- Discipline: mechanical / electrical / I&C / civil / chemistry / operations / RP

- Task family: inspection / disassembly / replacement / refurbishment / calibration / test / scaffold / clearance / restoration

- Component family: valve / breaker / transmitter / pump / instrument line / heat exchanger / snubber / motor

- Execution mode: routine / emergent / rework / vendor-supported / specialty

Then map plant-specific labels and abbreviations into this taxonomy. That alone may improve retrieval quality more than adding another NLP model.

4. Model uncertainty with mixture distributions. Do not assume one simple distribution for every task class. For many outage tasks, duration behavior is better represented as a mixture:

- baseline execution mode

- difficulty/escalated mode

- emergent/finding-driven mode

In other words, the task may have a normal “clean execution” duration most of the time, plus a lower-probability longer mode when inspection findings or coordination issues occur. That will produce more realistic tails than a single generic distribution.

5. Distinguish epistemic from aleatory uncertainty. Right now the paper discusses “variance” and duration distributions, but in practice you have two different uncertainty types:

- aleatory: true natural variability in execution time

- epistemic: lack of knowledge because the activity is poorly defined, rare, or badly matched in historical data

This distinction matters for actionability:

- If uncertainty is aleatory, maybe you add schedule protection.

- If uncertainty is epistemic, maybe you demand better work package definition, pre-job review, field walkdown, or SME review.

So each activity should return not just a duration distribution, but also a confidence score or evidence score:

- high-confidence estimate: many good historical analogs

- medium-confidence estimate: moderate analog coverage

- low-confidence estimate: weak analog coverage, expert review required

6. Add validation against outage-planning use cases. I would validate the approach on at least four tasks:

- Duration interval calibration: Does the observed actual duration fall inside the predicted P80 interval about 80% of the time?

- Critical path change detection: Can the tool identify non-CP tasks/strings that later become CP drivers?

- Planner override usefulness: When planners disagree with the tool, who is usually more accurate and under what conditions?

- Outage-level impact: If this method had been used on prior outages, how many delay days or schedule misses would have been prevented?

## Initial Development Plan

### Phase 1: Make the similarity engine operationally credible

- create a curated abbreviation and synonym library specific to outage language

- build a task taxonomy

- move to case-based retrieval with weighted similarity

- produce a confidence score for each estimate

- define fallback logic for sparse-data cases

### Phase 2: Improve the uncertainty model

- separate normal variability from disruption-driven tails

- account for plant/unit/context conditioning

- distinguish low-data uncertainty from real execution variability

- incorporate simple dependency structures between related tasks

### Phase 3: Make outputs usable by planners

For each planned task, return:

- recommended P50 / P80 / P90 duration

- confidence score

- top historical analogs used

- major drivers of uncertainty

- whether the task is a candidate for pre-outage mitigation

- whether it threatens a near-critical path

Phase 4: Evaluate with retrospective outage replay

Take several historical outages and ask:

- what would the tool have flagged before execution?

- which flags would have been correct?

- how much earlier would planners have seen the risk?

- what schedule changes would have been recommended?

## MAJOR COMMENTS

- Over-reliance on Text-Based Similarity. The current similarity approach is heavily dependent on semantic similarity of short activity descriptions. In practice, outage activity duration is strongly influenced by execution context (e.g., work environment, resource constraints, scaffolding, radiation protection requirements, emergent conditions). Two activities with similar text may have significantly different durations due to these factors. The method should incorporate structured contextual features beyond text.

- Lack of Context-Aware Case Representation Activities are treated primarily as textual entities rather than full “cases.” A more robust approach would represent each activity as a multi-dimensional case including discipline, component type, plant/unit, outage phase, dependencies, and execution conditions. Without this, similarity results risk being operationally misleading.

- Fragility of Similarity Thresholding. The use of a fixed similarity threshold (e.g., 0.7–0.9) introduces instability:

  - May yield too few matches for rare tasks

  - May include heterogeneous matches for common tasks

  - Highly sensitive to threshold tuning

A weighted nearest-neighbor approach would be more robust and scalable.

- Insufficient Treatment of Outliers and Heavy Tails. The current approach aggregates historical durations into a distribution without clearly distinguishing between:

  - Normal execution variability

  - Special-cause disruptions (e.g., emergent findings, rework)

Mixing these effects can distort the resulting distribution and reduce decision usefulness.

- No Explicit Confidence or Data Sufficiency Metric The method does not quantify confidence in the estimated duration distribution. In practice, planners need to know whether an estimate is based on strong historical analogs or weak/incomplete data.

- Missing Hierarchical Fallback Strategy. When no sufficiently similar activities are found, the approach lacks a clearly defined fallback hierarchy (e.g., plant-level → fleet-level → task class → generic prior → expert input). This is necessary for operational completeness.

- Limited Validation Against Operational Metrics. Evaluation focuses on correlation and qualitative assessment. There is no validation showing improvement in:

  - Schedule adherence

  - Critical path prediction accuracy

  - Reduction in outage delays

  - Decision-based validation is required.

- Independence Assumption in Uncertainty Propagation. The Monte Carlo propagation appears to treat activity durations as independent. In reality, many outage activities are correlated (shared crews, shared work areas, common constraints). Ignoring these dependencies may underestimate schedule risk.

- Underdeveloped Schedule-Level Metrics. The robustness metric (probability of finishing within baseline CP duration) is a good start but insufficient for decision-making. Additional actionable metrics are needed (e.g., probability of becoming critical, expected drag contribution, variance contribution).

- Weak Integration with Work Management Data. The approach acknowledges lack of linkage between activities and work orders. Without integration of richer work management data, the similarity method will remain limited in fidelity.

## MINOR COMMENTS

- Data Quality Issues Are Identified but Not Fully Quantified. The paper correctly highlights issues with abbreviations, spelling, and short descriptions, but does not quantify how much each issue degrades performance.

- Abbreviation Handling Approach May Be Ambiguous. The abbreviation expansion method relies on contextual matching but may introduce errors when abbreviations are overloaded. A domain-specific controlled vocabulary may be needed.

- Labeling Is Incomplete and Inconsistent. Approximately 30% of activities lack labels, and existing labels are plant-specific. This limits their usefulness in similarity computations.

- Computational Performance Not Characterized. The paper notes that similarity computation must be fast but does not provide performance benchmarks or scalability analysis.

- Limited Discussion of Data Volume Requirements The approach does not specify how much historical data is needed to produce reliable distributions for different task categories.

- No Clear Strategy for Cross-Plant Generalization While combining datasets from multiple plants is suggested, differences in practices and procedures may limit transferability.

- Visualization of Results Needs Enhancement. Histograms of duration distributions are useful but insufficient. Additional visualizations (e.g., confidence intervals, comparison to planned duration) would improve usability.

- ML Approach Conclusions Could Be Strengthened. The conclusion that ML cannot predict durations from short text is reasonable, but additional experiments (e.g., hybrid models) could reinforce this claim.

- Terminology: Robustness vs Resilience. The distinction is introduced but could be more consistently applied and operationally defined.

- Limited Discussion of User Interaction. The paper does not describe how planners would interact with the tool or interpret its outputs in real workflows.

## RECOMMENDED NEXT-STEP EXPERIMENTS

- Case-Based Similarity vs Text-Only Similarity. Develop a case-based representation including structured features (discipline, component, plant, dependencies, etc.) and compare performance against text-only similarity in predicting duration distributions.

- Weighted Nearest-Neighbor Retrieval. Replace threshold-based filtering with weighted retrieval (e.g., top-k similar activities with similarity-based weights). Evaluate stability and predictive accuracy.

- Confidence Scoring Framework. Define and test a confidence metric based on:

- Number of similar historical cases

- Similarity strength

- Consistency of retrieved durations

Assess how confidence correlates with prediction accuracy.

- Outlier and Mixture Modeling. Separate historical data into:

- Normal execution cases

- Disruption-driven cases

Fit mixture distributions and compare with single-distribution models in terms of predictive usefulness.

- Hierarchical Fallback Strategy. Implement a multi-level fallback system (plant → fleet → task class → generic prior) and evaluate coverage and performance across sparse data scenarios.

- Dependency-Aware Monte Carlo Simulation. Introduce correlation structures between related activities (e.g., shared crew, shared work area) and compare schedule risk estimates with independent sampling.

- Critical Path Prediction Accuracy. Evaluate whether the method can predict which non-critical activities or paths become critical during execution.

- Calibration of Duration Quantiles. Test whether predicted P50/P80/P90 durations are statistically calibrated (e.g., actual duration falls within P80 ~80% of the time).

- Retrospective Outage Replay. Apply the method to past outages and simulate what insights would have been available during planning:

- Identify missed risks

- Quantify potential reduction in delay days

- Integration with Work Management Data. Link activity records to work orders and evaluate improvement in similarity quality and duration prediction.

- Sensitivity Analysis of Similarity Weights. Vary the weights assigned to text similarity vs contextual features and assess impact on performance.

- Human-in-the-Loop Evaluation. Compare tool-generated estimates with expert planner estimates to identify strengths, weaknesses, and trust gaps.

- Scalability and Runtime Testing. Measure computation time for similarity search and Monte Carlo simulation on realistic datasets (tens of thousands of activities).

- User Interface Prototyping. Develop prototype visual outputs (e.g., risk dashboards, activity uncertainty flags) and conduct usability testing with outage planners.

- Cross-Plant Generalization Study. Train on one plant (or set of plants) and test on another to evaluate transferability and need for plant-specific tuning.

April 9th development

- [done] Phase 1 — Make the smoke test pass (fix the package + wire real text processing)

  - Fix pyproject.toml package structure so outage_uncertainty is importable

  - Wire dackar.text_processing.Preprocessing into ActivityCleaner

  - Wire dackar.text_processing.Abbreviation into AbbreviationResolver

  - Wire dackar.similarity.SentenceSimilarity into SemanticSimilarityScorer

- [done] Phase 2 — Make retrieval meaningful (case-based composite similarity)

  - Implement real HistoricalActivityIndex.search() with actual scoring

  - Upgrade ContextSimilarityScorer to proper weighted multi-field scoring

  - Replace hard threshold NeighborSelector with soft top-k

- [done] Phase 3 — Better uncertainty modeling

  - Implement outlier separation in OutlierHandler (trim vs. disruption mode)

  - Implement 3-tier confidence scoring (high/medium/low) based on support count + similarity

  - Implement hierarchical fallback chain

- Phase 4 — Task taxonomy

  - Populate TaskLabelMapper with outage-specific vocabulary (discipline, task_family, component_family)